## Time Slot
FUNCTIONALITY | TIME (ENGLISH) | TIME (ARABIC) | UI AND BROWSER COMPATIABILITY | TIME (ENGLISH) | TIME (ARABIC)
Hotel Search | 1 hour | 1 hour | Hotel Search | 2 hour | 2 hours
Result Page | 3 hours | 1 hour | Result Page | 3 hours | 3 hours
Room Listing Page | 2 hours | 1 hour | Room Listing Page | 2 hours | 2 hours
Customer Details Page | 2 hours | 1 hour | Customer Details Page | 2 hours | 2 hours
Payment Page | 2 hours | 1 hour | Payment Page | 2 hour | 2 hour
Gateway Page | 2 hours | 1 hour | Gateway Page | 1 hour | 1 hour
Ticket | 2 hours | 1 hour | Ticket | 2 hour | 2 hour
My Booking | 2 hours | 1 hour | My Booking | 2 hours | 2 hours
Total | 16 hours | 8 hours |  | 16 hours | 16 hours
UI and Brwoser compatiability test should include testing on dektop version, iPad and mobile divices (both android and iphone). IE, Chrome, Mozilla and Safari should be verified for browser compatiability

## Hotel Search
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | STATUS | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time: |  | Note -: Extra added points are highlighted in blue colour with bold text
HS 1 | HOTEL SEARCH
HS 1.1 | Destination | Search by hotel name/city (Location) | Should list city and hotel name with destination and should be selectable on click |  | PASS
|  |  | There should be a placeholder name present on the location entering field |  | PASS
|  |  | Atleast 7 location search suggesions should be displayed on the location search input field for a single word search |  | PASS
|  |  | There should be a location suggestion option scroll down option |  | PASS
|  |  | The selection for location suggession background should be highlighted in colour |  | PASS
|  |  | There should be mouse hover icon present for the location suggessions |  | PASS
|  |  | The Search suggesions should be starting with the search key keyword |  | FAIL
|  |  | The selected location should be displaed on the Location input field with bold letters |  | PASS
|  |  | There should be location coloured clear button with present on the location input field section |  | PASS
|  |  | While mouse hover over the Clear butto there should be hand icon present |  | PASS
|  |  | After selecting the desired location, the cursor pointer should not be present on the location input field section |  | PASS
|  |  | By clicking on the clear button the selected location should be removed with the clear button and the cursor indication for the input field should be displayed again |  | PASS
|  |  | Priority on the list should be provided to City |  | PASS
|  |  | After selecting the desired location, the Check in date selection should be automatically selected |  | PASS
HS 1.2 | Check in date | Click on check in field | The calander should be displayed (Atleast 2 months together) |  | PASS
|  |  | Current date must be highlighted on the calender |  | PASS
|  |  | System should not show or should not be selectable a date earlier than current date (Earlier dates should be disabled) |  | PASS
|  |  | Earlier month navigation button should be disabled with respect to current date |  | PASS
|  |  | There should be a placeholder name present on the Check in date |  | PASS
|  |  | The Selected date ,month and year should be displayed on the Check in date section |  | PASS
|  |  | The selected date should be highlighted in different colour |  | PASS
|  |  | There should be a mousehover pointer with selection colour change present on the Check in date |  | PASS
|  |  | The dates from 1 to 9 should be displayed with an extra Zero as prefix |  | PASS
|  |  | The Check in date calender should be start from the Check in date position itself |  | PASS
|  |  | The Check in date and Check out date should not be same , atleast one day difference should be present |  | PASS
|  |  | After selecting theCheck in date, the Check in date selection should be automatically selected |  | PASS
|  |  | The calender should pop up when click on any where around the Check in date feild |  | PASS
HS 1.3 | Check out date | Click on check out field | The calander should be displayed |  | PASS
|  |  | Allow to select check out date which is not earlier than check in date |  | PASS
|  |  | Earlier month navigation button should be disabled with respect to current date |  | PASS
|  |  | There should be a placeholder name present on the Check out date |  | PASS
|  |  | The Selected date ,month and year should be displayed on the Check out date section |  | PASS
|  |  | The selected date should be highlighted in different colour |  | PASS
|  |  | There should be a mousehover pointer with selection colour change present on the Check out date |  | PASS
|  |  | The dates from 1 to 9 should be displayed with an extra Zero as prefix |  | PASS
|  |  | The Check out date calender should be start from the Check out date position itself |  | PASS
|  |  | After selecting the Check out date, the Nationality field should be automatically selected |  | PASS
|  |  | The calender should pop up when click on any where around the Check out date feild |  | PASS
HS 1.4 | Nationality | On selection | By default nationality as kuwait is shown and should be able to select the nationality from the drop down list |  | PASS
|  |  | There should be a placeholder name present on the Nationality input field |  | PASS
|  |  | Atleast 7 Nationality search suggesions should be displayed on the Nationality search input field for a single word search |  | PASS
|  |  | There should be a Nationality suggestion option scroll down option |  | PASS
|  |  | The selection for Nationality suggession background should be highlighted in colour |  | PASS
|  |  | There should be mouse hover icon present for the Nationality suggessions |  | PASS
|  |  | The Search suggesions should be starting with the search key keyword |  | PASS
|  |  | The selected Nationality should be displaed on the Nationality input field with bold letters |  | PASS
|  |  | There should be Nationality coloured clear button with present on the Nationality input field section |  | PASS
|  |  | While mouse hover over the Clear butto there should be hand icon present |  | PASS
|  |  | After selecting the desired Nationality, the cursor pointer should not be present on the Nationality input field section |  | PASS
|  |  | By clicking on the clear button the selected Nationality should be removed with the clear button and the cursor indication for the input field should be displayed again |  | PASS
|  |  | By selectiong on a large Nationality name , it should should display the "…" 3 dots continues symbol and should not overlaps the Nationality field |  | PASS
By clicking on the Search button with blank Nationality should shows a validation "Please Select Nationality"
| Country of Residence | On selection | Bydefault country of residence as kuwait and Should be able to select the country of residence from the drop down list |  | PASS
HS 1.5 | Room (Guest & Room) | On selection | By default two room should be selected. Should be able to select upto 5 rooms |  | PASS
|  |  | It should show Adult and child selection option for one room |  | PASS
|  |  | The Guest & Room should be a drop down selection |  | PASS
|  |  | The (Guest & Room) should pop up when click on any where around the (Guest & Room) feild |  | PASS
|  |  | By default one room with 1 adult guest should be selected and Should be able to select upto 5 rooms |  | PASS
|  |  | There should be an "Add room +" button inside the Guest & Room drop down |  | PASS
|  |  | There should be a "Apply button" present inside the Guest & Room drop down |  | PASS
|  |  | There should be no. for each room (eg. Room 1) |  | PASS
|  |  | By clicking on the "Add room +" button , there should be additional room option should be displyed inside the drop down |  | PASS
|  |  | The "Add room +" button should be present untill we add 5 rooms |  | PASS
|  |  | The "- Remove Room" button should be displayed on Guest & Room drop down |  | PASS
|  |  | By clicking on the "- Remove Room" the last added room should be removed |  | PASS
|  |  | By clicking on the Appy button the droip down should be collapsed |  | PASS
|  |  | The "Add room +" button should be removed while the room count reaches to 5 |  | PASS
|  |  | The "- Remove Room" button should be removed while there is only one room is present |  | PASS
|  |  | There should be a dedicated close button for the Guest & Room drop down |  | PASS
|  |  | The Total no. of guest should be updated on th Guest & Room field on real time |  | PASS
|  |  | All the buttons "+,-,+ Add Room , - Remove Room , Apply" should have a hand mouse pointerv while mouse hover it abd animation of movement like actual button |  | PASS
PASS
PASS
HS 1.5.1 | Guest Count | On selection of Adult | Should be able to select a maximum of 5 adults per room |  | PASS
|  | On selection of child | Should have option to select child upto 2 per room |  | PASS
|  | Select one child | Option should be there to enter child age ( 0 -11 Years) |  | PASS
|  | Select two child | Option should be displayed to enter the second child age |  | PASS
|  |  | There should be "+" and "-" button resent for adding and reducing the Adult and infant count |  | PASS
|  |  | There should be Age range displayed for both adult and child |  | PASS
|  |  | By default the child count should be zero |  | PASS
|  |  | By selecting one child , a age adding and minusing option should be present |  | PASS
|  |  | The child age should be selected from 0-11 years |  | PASS
HS 1.5.2 | Multiple Room | Select two room from the Room option | Option should be displayed to enter adult and child count for two room. |  | PASS
|  | Select five room from the Room option | Option should be displayed to enter adult and child count for five room |  | PASS
| Add room/Remove room | on selection | Add room- to add number of rooms |  | PASS
|  |  | Remove room - to remove the number of rooms |  | PASS
HS 1.5.3 | Star rating | On selection | should be able to select upto 5 star ratings |  | PASS
| Search button | On selection | it will redirect to hotel result page |  | PASS
|  |  | By clicking on the Search button with blank location should shows a validation "Enter valid city name" |  | PASS
| Recent searches | On display | shows the search scenarios having location, check in date and check out date |  | PASS
|  | On selection | it will redirect to hotel result page |  | PASS
HS 1.6 | Validations
HS 1.6.1 | Destination/Hotel name | If not entered | Display alert to enter destination |  | PASS
|  | If wrong destination entered/not selected from drop-down list | Display alert to enter correct destination/hotel name |  | PASS
|  | If extra space added on the destination | System should auto-trim the extra space |  | PASS
HS 1.6.2 | Check in and Check out Date | If Check in date not entered | Display alert to enter check in date |  | PASS
|  | If check out date not entered | Display alert to enter check out date |  | PASS
HS 1.6.3 | Nationality | If Nationality not entered | Display alert to enter Nationality |  | PASS

## Hotel Result
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | STATUS | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time:
HR 1 | HOTEL RESULT | Select single room 1 adult and 1 child from the search page and serach for the destination Dubai | Should display all the available hotels results on Dubai destination for Single room, 1 adult and 1 child |  | pass
|  | On Display | Should display the available number of results above the sorting option (if applicable) |  | pass
|  |  | Should display the search summary (Destination, Check in, check out date, number of rooms and pax count) next to the total availabe room count (if applicable) |  | pass
|  |  | Display hotel image for each available hotel, if image is not provided by the API, display standard 'No image Available' text |  | pass
|  |  | Display hotel star sating of each available hotel |  | pass
|  |  | Display hotel Address of each available hotel |  | pass
|  |  | Display a small description about the hotel of each available hotel |  | pass
|  |  | Display Details, Map and facilities menu on each available hotel |  | Fail | Facilities is missing
|  |  | Show the per room/ night price of the hotel (by default it should display in the base currecy) |  | pass
|  | On selecting the Details menu | Popup with Hotel details and description |  | Fail
|  |  | A 'X' button should be there to close the pop up |  | Fail
|  | On selecting the Map menu | It should diaply the Map of that particular hotel |  | pass
|  |  | A 'X' button should be there to close the map |  | pass
|  | On selecting the Facilities menu | It should display the facilities of that particular hotel |  | Fail
|  |  | A 'X' button should be there to close the photo popup |  | Fail
|  | On selecting the 'Select' button | Should load the next page with selected hotel information like available rooms in that hotel based on the search criteria, Hotel photos, hotel map, hotel description |  | pass
|  |  | The Details menu , Map menu , Facilities menu are should be switched from each other |  | Fail
HR 2 | SORTING
|  |  | There should a drop down with Name , Price , Rating sorting option should be displayed |  | pass
|  |  | By clicking outside the sorting drop down , the drop down should be collapsed back |  | pass
|  |  | At a time there should be one sorting arrow should be selected |  | pass
|  |  | The Sorting optionn selected should display both the sorting name and the up/down arrow |  | pass
HR 2.1 | Name | Ascending Order | The hotel name will be sorted in the order A-Z and the arrow icon should be highlighted up/down |  | pass
|  | Descending Order | The hotel name will be sorted in the order Z-A and the arrow icon should be highlighted up/down |  | pass
HR 2.2 | Price | Ascending Order | The results price will be sorted from lowest to highest and the arrow icon should be highlighted up/down |  | pass
|  | Descending Order | The results price will be sorted from highest to lowest and the arrow icon should be highlighted up/down |  | pass
HR 2.3 | Star Rating | Ascending Order | The results star rating will be sorted from one to five and the arrow icon should be highlighted up/down |  | pass
|  | Descending Order | The results star rating will be sorted from five to one and the arrow icon should be highlighted up/down |  | pass
HR 3 | FILTER
HR 3.1 | Price | Move the filter from left to right (lowest price to highest price) | The lowest priced results will get removed from the result page and the total result count will get updated based on the removed number of results. |  | NA
|  | Move the filter from right to left (highest price to lowest price) | The highest priced results will get removed from the result page and the total result count will get updated based on the removed number of results. |  | NA
|  |  | There should be the check boxed with multiple price ranges |  | pass
|  |  | The no. of counts of hotel results in bracket should be diplayed besides the price range check boxes |  | pass
|  |  | The selected check box should be highlighted with a tick mark |  | pass
|  |  | There should be clear button present from removing all applied the price filters together |  | pass
|  |  | The result should be with in the price range selected |  | pass
|  |  | The filter can be selected when click on the price range text |  | pass
HR 3.2 | Star Rating | Star Rating Checked | The results should display the checked star hotels and the total result count should get updated based on it. |  | pass
|  | Star Rating Unchecked | The results should not display the unchecked star hotels and the total result count should get updated based on it. |  | pass
|  | All Star Rating Checked | Display all the results |  | pass
|  | All Star Rating Unchecked | Display all the results |  | pass
|  | Click on the clear button | It should clear the entry and should list all the available hotels |  | pass
|  |  | The selected star rating should be highlighted |  | pass
|  |  | Should be able to select multiple star rating |  | pass
HR 3.3 | Filter by name
|  |  | There should be a Search Hotels input field present |  | pass
|  |  | By searching with key word on the Search Hotels input field the result should be shows on the suggession |  | pass
|  |  | There should be a clear button present on the Search Hotels input field |  | pass
|  |  | The hotel should be highlighted while mouse hover over the hotel suggessions and there should be mouse pointer hand icon |  | pass
|  |  | There should be sroll down option present to navigate all hotel results |  | pass
|  |  | The result suggessions should be in alphabetic order |  | pass
|  |  | There should be a validation present while searching with blank search hotel |  | NA
|  | Enter hotel name | It should auto display the available hotels as the user type |  | pass
|  | Select a hotel and click on search icon | It should display the selected hotel only in the result page and the result count should get updated accordingly |  | pass
|  | Click on the clear button near to filter by name | It should clear the entry and should list all the available hotels |  | pass
HR 3.4 | Filter by location
|  | Enter hotel location | It should auto display the available hotels as the user type |  | NA
|  | Select a hotel location and click on search icon | It should display the selected hotel corresponding to hotel location only in the result page and the result count should get updated accordingly |  | NA
|  | Click on the clear button near to filter by location | It should clear the entry and should list all the available hotels |  | NA
HR 4 | VIEW ON MAP
|  | On selection | It should show all the hotel results in a single map |  | pass
|  |  | On selection it should show a pop up with hotel image, name, star rating, address and per room per night price. Option should be there to select the hotel |  | pass
|  |  | The text View on Map should be replaced with 'List View" |  | NA
|  | On selecting the hotel from the pop up | It should take the user to next page with room details, images, map and hotel description |  | pass
HR 5 | LIST VIEW | On selecting List view | The Map view should be switch back to normal result display |  | NA
HR 6 | CURRENCY | Select another currecy from the header | The price should be changed to the selected currency |  | pass
HR 7 | MODIFY SEARCH | On selection | By deafult it should display the search criteria entred on home page search panel |  | pass
HR 7.1 | Destination | Search by hotel name | Should list the hotel name with destination and should be selectable on click |  | pass
|  | Search by City | Should list the city name and should be selectable on click |  | pass
HR 7.2 | Check in date | Click on check in field | The calander should be displayed |  | pass
|  |  | Current date must be highlighted on the calender |  | pass
|  |  | System should not show or should not be selectable a date earlier than current date |  | pass
HR 7.3 | Check out date | Click on check out field | The calander should be displayed |  | pass
|  |  | Allow to select check out date which is not earlier than check in date |  | pass
HR 7.4 | Nationality | On selection | Should be able to select the nationality from the drop down list |  | pass
HR 7.5 | Room | On selection | By default one room should be selected.Should be able to select upto 5 rooms |  | pass
|  |  | It should show Adult and child selection option for one room |  | pass
HR 7.5.1 | Guest Count | On selection of Adult | Should be able to select a maximum of 5 adults per room |  | pass
|  | On selection of child | Should have option to select child age upto 2 per room |  | pass
|  | Select one child | Option should be there to enter child ( 1 -11 Years) |  | pass
|  | Select two child | Option should be displayed to enter the second child age |  | pass
HR 7.5.2 | Multiple Room | Select two room from the Room option | Option should be displayed to enter adult and child count for two room. |  | pass
|  | Select five room from the Room option | Option should be displayed to enter adult and child count for five room |  | pass
HR 8 | MULTIPLE ROOM | Select 3 rooms; in room one select 2 adult, one child, in room two select one adult and one child and in room three select 3 adult from the search page and serach for the destination Dubai | Should display all the available hotels results on Dubai destination for 3 rooms, 6 adults and 2 child |  | pass
HR 8.1 | Price | On display | It should display the price per night |  | pass
HS 10 | VALIDATIONS
HS 10.1 | Destination/Hotel name | If not entered | Display alert to enter destination |  | pass
|  | If wrong destination entered/not selected from drop-down list | Display alert to enter correct destination/hotel name |  | pass
|  | If extra space added on the destination | System should auto-trim the extra space |  | Fail
HS 10.2 | Check in and Check out Date | If Check in date not entered | Display alert to enter check in date |  | pass
|  | If check out date not entered | Display alert to enter check out date |  | pass
HS 10.3 | Nationality | If Nationality not entered | Display alert to enter Nationlaity |  | pass

## Room Listing Page
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | PASS | FAIL | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time:
HL 1 | SINGLE ROOM | Select a hotel from the hotel result page for Single room, one adult and one child | It should direct the user to room listing page | it directs to room listing page | pass
|  | On display | Should display the hotel name, star rating and address at the top | displays the hotel name, star rating and address at the top | pass
|  |  | Available hotel images should be shown and one image should be enalrged, on selection, the selected photo should replace the enlarged image |  | pass
|  |  | Map of the hotel should be displayed |  | pass
|  |  | All the available room should be displayed |  | pass
|  |  | Hotel highlights and overview should be displayed |  | pass
HL 1.1 | Available Rooms | On display | Each availabel room name and board type should be displayed with thumbnail image |  | pass
|  |  | Cancelation policy should be displayed |  | pass
|  |  | Guest count (one adult and one child) should be dipalyed with icons (Adult with adult icon and child with child icon) |  | pass
|  |  | Total price (for the total number of nights) should be displayed |  | pass
|  |  | 'Book' option should be there to select the required room |  | pass
|  |  | 'Continue' button should be there to proceed to next page (if applicable) |  | NA
|  | On click on 'cancellation policy' link | It should display a pop up with the cancellation policy details with close button |  | pass
|  |  | on clicking X button , cancellation policy popup will get closed |  | pass
HL 2 | MULTIPLE ROOM | Select a hotel from the hotel result page for tripple room, one adult and one child for first room, two adult for second room, and two adult and two child for third room | It should take the user to room listing page |  | pass
|  | On display | Should display the hotel name, star rating and adress at the top |  | pass
|  |  | Available hotel images should be shown and one image should be enalrged, on selection, the selected photo should replace the enlarged image |  | pass
|  |  | Map of the hotel should be displayed |  | pass
|  |  | All the available room should be displayed |  | pass
|  |  | Hotel highlights and overview should be displayed |  | pass
HL 2.1 | Available Rooms- Separate Room | On display of Room 1 | Room 1 heading should be there |  | pass
|  |  | Each availabel room name and board type should be displayed with thumbnail image |  | pass
|  |  | Cancelation policy link (in a different colour preferabily green or red) should be displayed |  | pass
|  |  | Guest count (one adult and one child) should be dipalyed with icons (Adult with adult icon and child with child icon) |  | pass
|  |  | Total price (for the total number of nights) should be displayed |  | pass
|  |  | 'Book' option should be there to select the required room |  | pass
|  | On click on 'cancellation policy' link | It should display a pop up with the cancellation policy details |  | pass
|  | On click on 'Book' button | The room should get selected and all other rooms should be hidden |  | NA |  | not present in attar
|  |  | The 'Book' button should be replaced with 'Change' button |  | NA |  | not present in attar
|  | On click on 'Change' button | The selected room should get deselected and all available rooms should be displayed |  | NA |  | not present in attar
|  | On display of Room 2 | Room 2 heading should be there |  | NA |  | not present in attar
|  |  | Each available room name and board type should be displayed with thumbnail image |  | NA |  | not present in attar
|  |  | Cancelation policy link should be displayed |  | NA |  | not present in attar
|  |  | Guest count (two adult) should be dipalyed with icons (Adult with adult icon) |  | NA |  | not present in attar
[5 empty] | NA |  | not present in attar
|  |  | Total price (for the total number of nights) should be displayed |  | NA |  | not present in attar
|  |  | 'Book' option should be there to select the required room |  | NA |  | not present in attar
|  | On click on 'cancellation policy' link | It should display a pop up with the cancellation policy details |  | pass
|  | On click on 'Book' button | The room should get selected and all other rooms should be hidden |  | NA
|  |  | The 'Book' button should be replaced with 'Change' button |  | NA
|  | On click on 'Change' button | The selected room should get deselected and all available rooms should be displayed |  | NA
|  | On display of Room 3 | Room 3 heading should be there |  | NA
|  |  | Each availabel room name and board type should be displayed with thumbnail image |  | pass
|  |  | Cancelation policy link should be displayed |  | pass
|  |  | Guest count (two adult and two child) should be dipalyed with icons (Adult with adult icon and child with child icon) |  | pass
pass
|  |  | Total price (for the total number of nights) should be displayed |  | pass
|  |  | 'Book' option should be there to select the required room |  | pass
|  | On click on 'cancellation policy' link | It should display a pop up with the cancellation policy details |  | pass
|  | On click on 'Book' button | The room should get selected and all other rooms should be hidden |  | NA
|  |  | The 'Book' button should be replaced with 'Change' button |  | NA
|  | On click on 'Change' button | The selected room should get deselected and all available rooms should be displayed |  | NA
|  | On click on 'continue' button | It should take the user to guest details page |  | NA
HL 2.2 | Available Rooms- Combined Room | On display | It should display the combination of 3 rooms as options like option 1, option 2 |  | pass
|  |  | Should display each room type, board type in the combination provided |  | pass
|  |  | Guest count in each room based on the search criteria (one adult and one child for first room, two adult for second room, and two adult and two child for third room) should be displayed |  | pass
|  |  | total night price should be displayed |  | pass
|  |  | There be should only a single cancellation policy per room combination |  | fail |  | there is seperte cancelation policy
|  | On click on 'cancellation policy' link | It should display a pop up with the cancellation policy details |  | pass
|  | On click on 'Book' button | The room should get selected and all other rooms should be hidden |  | NA
|  |  | The 'Book' button should be replaced with 'Change' button |  | NA
|  | On click on 'Change' button | The selected room should get deselected and all available rooms should be displayed |  | NA
|  | On click on 'continue' button | It should take the user to guest details page |  | NA
NA
| ADD TO CART | on click on add to cart | The selected room should be added to cart |  | NA
| BACK BUTTON | On display | By deafult it should display the search criteria entred on home page search panel |  | pass
|  | On selection | it should redirect to hotel result page |  | NA
HL 3 | CUREENCY | On Display | It should display the currency which is shown in the result page |  | pass
|  | Select a different currecy from the result page and proceed to room listing page | It should diplay the price in the selected currency |  | pass
HL 4 | BACK TO RESULT | Click the back to result button | It should take the user to result page |  | pass
HL 5 | BREADCRUMBS | On display | The breadcrumbs should be displayed and the 'Selection' should be highlighted to indicate the user is on room selection page |  | NA

## Pax and payment Page
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | PASS | FAIL | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time:
HG1 | HOTEL SUMMARY | On display | A summary of the selected hotel should be displayed |  | PASS
|  |  | Hotel name |  | PASS
|  |  | Hotel address |  | PASS
|  |  | Hotel image |  | PASS
|  |  | Check in |  | PASS
|  |  | Check Out |  | PASS
|  |  | No. of rooms and nights |  | PASS
|  |  | No. of persons |  | PASS
|  |  | Total price and cancellation policy |  | PASS
HG 1.1 | Change this hotel | on selecting Change this hotel | Should take the user back to the hotel result page |  | NA
HG 2 | Back button | Select the button back | Should take the user back to room listing page |  | PASS
|  | On selection of another Hotel | Selected Hotel details should be displayed in the summary |  | PASS
| BREADCRUMBS | On display | The breadcrumbs should be displayed and the 'Selection' should be highlighted to indicate the user is on room selection page |  | NA
HG 3 | LOGIN OR SIGN UP |  | Allow the customer to login/register and continue with the booking |  | PASS
HG 3.1 | Login | On selection | Should show the login section as expand and collapse option |  | PASS
HG 3.1.1 | Correct Data | Enter correct user name and password | Successful login and auto populate pax details |  | PASS
HG 3.1.2 | Wrong Data | Enter wrong user name and password | Login failure with message "Invalid user name or password" |  | PASS
HG 3.1.3 | Forgot Password | On selection | Should load forgot password pop up: E mail ID filed should be there in the pop up and a close button to close the pop up |  | PASS
|  | Enter registered e mail ID | Should receive an e mail with a password resetting option on the registered e mail ID |  | PASS
|  | Enter a not registered e mail ID | Show the message "The given e mail ID is not registered on the site" |  | PASS
|  | Validation | Show message 'Invalid E Mail ID" if wrong e mail ID is entered |  | PASS
HG 3.2 | Sign up | On selection | Should load the register pop up with a close button to close the pop up. |  | PASS
HG 3.2.1 | With all required information | Enter following mandatory information: First Name, Last Name, E mail ID, Phone number with country code and Password | Successful registration message 'You have successfully registered' |  | PASS
HG 3.2.2 | With partial information | If any information is missing | Alert to enter respective mandatory information |  | PASS
HG 3.2.3 | Validation | Second registration with same e mail ID/User Name | Alert message "Already registered E mail ID" |  | PASS
|  | Enter wrong e mail ID | Alert message "Invalid E Mail ID" |  | PASS
|  | Wrong/Invalid Phone Number | Alert message "Invalid phone number" |  | PASS
HG 3.2.4 | E mail confirmation | On successful registration | A confirmation e mail should be send to the registered e mail ID |  | PASS
| FACEBOOK | on selection | Login the pax page using facebook account |  | PASS
| GOOGLE | On selection | Login the pax page using google account |  | PASS
HG 4 | CONTINUE WITHOUT LOGIN |  | Passenger information fields will be blank and the user has to enter all the details. |  | PASS
HG 5 | CONTINUE WITH LOGIN | On successful login | All the required saved details of the passenger on 'MY PROFILE' will be auto populated on the passenger details filed |  | PASS
HG 6 | PASSENGER DETAILS- SINGLE ROOM | On Display of Single room with one adult and one child | Room 1 heading should be there with number of adults and child in that room. |  | PASS
HG 6.1 | Title | Adult | Should be able to select a title from Mr., Ms, Mrs, Miss |  | PASS
|  | Child | Should be able to select the title from the option Mstr and Miss |  | PASS
HG 6.2 | Name | First Name | Minimum two and maximum 23 alphabets |  | PASS
|  | Last Name | Minimum two and maximum 28 alphabets |  | PASS
HG 6.2.1 | Name Validations | Enter any special character or number | Show validation "Only alphabets are allowed" |  | PASS
|  | Enter characters greater than 51 | Show validation "Maximum character length for first, middle and last name combined should be less than 51" |  | PASS
|  | Enter same name for more than one pax | Show validation "Name should be unique for each passenger" |  | PASS
|  | Enter space with name | The system should auto-trim the space |  | FAIL
HG 7 | PASSENGER DETAILS- MULTIPLE ROOM | On Display of t room with one adult and one child in first room and two adults in second room | Room 1 heading should be there with number of adults(1) and child (1) in that room. |  | PASS
|  |  | Room 2 heading should be there with number of adults(2) in that room. |  | PASS
HG 7.1 | First Room | Adult title | Should be able to select a title from Mr., Ms, Mrs, Miss or Male or Female |  | PASS
|  | Adult- First Name | Minimum two and maximum 23 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
|  | Adult - Last Name | Minimum two and maximum 28 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
|  | Child titel | Should be able to select a title from Mr., Ms, Mrs, Miss or Male or Female |  | PASS
|  | Child- First Name | Minimum two and maximum 23 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
|  | Child- Last Name | Minimum two and maximum 28 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
HG 7.2 | Second Room | First adult title | Should be able to select a title from Mr., Ms, Mrs, Miss or Male or Female |  | PASS
|  | First Adult- First Name | Minimum two and maximum 23 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
|  | First Adult - Last Name | Minimum two and maximum 28 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
|  | Second adult title | Should be able to select a title from Mr., Ms, Mrs, Miss or Male or Female |  | PASS
|  | Second Adult- First Name | Minimum two and maximum 23 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
|  | Second Adult - Last Name | Minimum two and maximum 28 alphabets |  | FAIL |  | accepts upto 40 and no limit for last name
HG 8 | Mobile Number | Country code selection | Should display the drop down with Nation and Country phone code. Should allow the user to select the code. |  | PASS
|  | Enter numbers | Allow to proceed. |  | PASS
|  | Validation | Minimum length of 5 and maximum 15 |  | PASS
HG 9 | E Mail | Enter correct e mail ID | Allow to proceed. |  | PASS
|  | Enter wrong email ID | Show validation "Enter correct e mail ID" |  | PASS
|  | Enter space with e mail ID | The system should auto-trim the space |  | FAIL
|  | Select a different currecy from result page and proceed till guest details page | The price should be displayed in the selected currecy |  | FAIL
| Add Traveller to list/view saved Traveller details | display add traveller to list/view saved traveller details | On clicking add to traveller list, it will shows popup with first name,last name, email id,mobile number with countrycode |  | NA
|  |  | On clicking view saved traveller details, it shows the saved customer details. |  | NA
| COUPON CODE | Option to enter coupon code | Enter correct coupon code and click on apply, amount will be deducted from the total
|  | Invalid coupon code | If entered invalid coupon code and click on apply button, validation message is shown.
|  | Fare details | Shows price and total fare
Ensure the fare shown under fare details section are correct
| LOYALTY POINTS | Option to enter the points | Enter correct loyalty points and click on apply, amount will be deducted from the total |  | NA
|  |  | If entered points exceeds the current limit, system should not allow to proceed |  | NA
| CONTINUE | Enter all the pax details and proceed | Proceed to next page: Payment page |  | PASS
|  | Partially fill the pax details and proceed | Show validation on the missing / wrong data fields and don't allow to procced to pax page |  | PASS
|  | Click pay now after checking the terms and condition of cancellation policy check box | Take the user to select the payment gateway |  | PASS
| CHOOSE PAYMENT METHOD |  | Display the payment option available |  | PASS
|  |  | Show one payment gateway selected by default |  | PASS
|  |  | Display the selected payment gateway charge and total price |  | PASS
|  | Select another payment gateway | Show the payment gateway charge configured for that payment gateway |  | PASS
|  |  | The total price should be updated as per the payment gateway charge |  | PASS
|  | Click pay now with out checking the terms and condition check box | Show alert message 'Please agree to the terms and conditions |  | PASS
|  | Click pay now after checking the terms and condition check box | Take the user to selected payment gateway page |  | PASS
| FARE UPDATE | If the price got updated | Will show the price update pop up message with proceed and cancel option |  | PASS
|  |  | Fare summary should get updated with the new price |  | PASS
|  |  | On 'Proceed', will create the booking and will take the customer to payment gateway page |  | PASS
|  |  | On 'Cancel', will keep the customer on payment page itself |  | PASS
| E MAIL NOTIFICATION | On successful redirection | Admin should receive e mil: Redirected to payment gateway
|  | On failure | Admin should receive e mail: Not redirected payment gateway
| BOOKING FAILURE | On booking failure | Show the message, 'Sorry, an error occured. Please Try Again' |  | PASS
|  | On selection of 'Try Again' | Take the user to Result Page |  | PASS

## Gateway Page
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | PASS | FAIL | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time:
HG1 | GATEWAY PAGE - K NET |  | Show the final price on the gateway page |  | pass
|  | Enter correct card details | Payment success and redirect to website |  | pass
|  | Enter wrong details | Payment fails and redirect to Try Again website page |  | pass
|  | On selection of Cancel | Redirect to Try Again Page. |  | pass
HG 1.1 | TRY AGAIN PAGE |  | Gateway transaction details and Try again option |  | pass
|  | On cancellation from gateway page | Try again page will have the message 'Your payment attempt is canceled' with the transaction ID details and Try again option |  | pass
|  | On payment failure from gateway page | Try again page will have the message 'Your payment attempt is failed' with the transaction ID details and Try again option |  | pass
|  | On Try Again selection | Redirect to Payment Page |  | pass
|  | On selection of Pay Now | Will redirect to the selected payment page. The same booking ID (Payment initiated status on admin) will be used |  | pass
|  | On selection of Pay Now after editing guest information | Will redirect to the selected payment page. New booking ID (Payment initiated status on admin) will be created |  | pass
|  | On selection of Pay Now after changing the room | Will redirect to the selected payment page. New booking ID (Payment initiated status on admin) will be created |  | pass
|  | On selection of Pay Now after changing the hotel and room | Will redirect to the selected payment page. New booking ID (Payment initiated status on admin) will be created |  | pass
HG 1.2 | E MAIL NOTIFICATIONS | On successful Transaction | Admin should receive two mails
1.Payment done initiate booking
2.Payment success booking success
Customer will receive e mail with successful payment transaction details.
|  | On payment failure | Admin will receive Payment failure notification
Customer will receive e mail with failed payment transaction details
HG 2 | GATEWAY PAGE - CREDIT CARD(visa credit,visa debit,master credit,master debit,Tap) |  | Show the final price on the gateway page |  | pass
|  | Enter correct card details | Payment success and redirect to website |  | pass
|  | Enter wrong details | Payment fails and redirect to Try Again website page |  | pass
|  | On selection of Cancel | Redirect to Try Again Page. |  | pass
HG 2.1 | TRY AGAIN PAGE |  | Gateway transaction details and Try again option |  | pass
|  | On cancellation from gateway page | Try again page will have the message 'Your payment attempt is canceled' with the transaction ID details and Try again option. |  | pass
|  | On payment failure from gateway page | Try again page will have the message 'Your payment attempt is failed' with the transaction ID details and Try again option |  | pass
|  | On Try Again selection | Redirect to Payment Page |  | pass
|  | On selection of Pay Now | Will redirect to the selected payment page. The same booking ID (Payment initiated status on admin) will be used |  | pass
|  | On selection of Pay Now after editing guest information | Will redirect to the selected payment page. New booking ID (Payment initiated status on admin) will be created |  | pass
|  | On selection of Pay Now after changing the room | Will redirect to the selected payment page. New booking ID (Payment initiated status on admin) will be created |  | pass
|  | On selection of Pay Now after changing the hotel and room | Will redirect to the selected payment page. New booking ID (Payment initiated status on admin) will be created |  | pass
HG 2.2 | E MAIL NOTIFICATIONS | On successful Transaction | Admin should receive two mails
1.Payment done initiate booking
2.Payment success booking success
Customer will receive an e mail with Payment Transaction details
|  | On payment failure | Admin will receive Payment failure notification
Customer will receive e mail with failed payment transaction details

## Voucher
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | PASS | FAIL | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time:
HV 1 | HOTEL VOUCHER |  | Voucher should display below points
HV1.1 | SINGLE ROOM | On Display of voucher with single room with one adult and one child | Logo and Contact Details of the Agency |  | pass
|  |  | Booking reference number |  | pass
|  |  | Hotel details table |  | pass
|  |  | Hotel name, image and address |  | pass
|  |  | Check in date and check out date |  | pass
|  |  | No. of nights |  | pass
|  |  | No of rooms as one |  | pass
|  |  | Guest details table |  | pass
|  |  | Room 1 with room name should be displayed |  | pass
|  |  | Name of each guest in room 1 should be displyed |  | pass
|  |  | Date of issue, and each guest type (Adult or Child) should be displayed |  | pass
|  |  | Hotel confirmation number should be displayed (if applicable) |  | NA
Payment details table
|  |  | Payment amount charged should be displayed |  | pass
shows book transfers section
shows download qgo app
|  |  | Rules and Conditions should be displayed |  | pass
HV 1.2 | MULTIPLE ROOM | On Display of two room with one adult and one child in first room and two adults in second room | Logo and Contact Details of the Agency
Booking reference number
Hotel details table
Hotel name and address and Hotel image
Check in date and check out date
No. of nights
No of rooms as one
Guest details table
Room 1 with room name and board type should be displayed
Name of each guest in room 1 (1 adult and 1 child) should be displyed
Date of issue, hotel confirmation number and each guest type (Adult or Child) should be displayed
Room 2 with room name and board type should be displayed
Name of each guest in room 2 (2adults) should be displyed
|  |  | Date of issue, hotel confirmation number (if applicable) and each guest type (Adult) should be displayed |  | NA
Payment details table
Payment date and amount charged should be displayed
show Book transfers section
shows download qgo app
| PRINT VOUCHER | on click on print icon | should display voucher with print option |  | pass
| DOWNLOAD VOUCHER | on click on download icon | should download the voucher in pdf format |  | pass
| EMAIL VOUCHER | on click on email icon | should display an popup to enter email id for sending the voucher |  | pass
HV 1.3 | AMOUNT CHARGED | On display by enabling Show price in vocuher | Should display the price on the voucher
|  | On display by disabling Show price in vocuher | Should not display price on the voucher
|  | On display by enabling payment gateway charge in voucher | Should display the hotel charge including the payment gateway charge
|  | On display by disabling payment gateway charge in voucher | Should display the hotel charge including the payment gateway charge
HV 1.4 | PRINT | Click Print option | Should show the print popup and should be able to take the print out of the voucher |  | pass
HV 1.4 | VOUCHER FAILURE | On voucher failure | Customer will get a message saying "Sorry, we have encountered an error while processing your voucher. The amount'XXX' will be refunded to you. Please contact our customer care '+965 XXXXX' for immediate assistance"
HV 1.5 | E MAIL NOTIFICATIONS | On successful voucher | Admin will receive voucher notification
|  |  | Customer will receive e mail with E Voucher |  | pass
|  | On voucher failure | Admin will receive voucher failure notification

## My Booking
CASE ID | MODULE | TEST STEP | EXPECTED RESULT | ACTUAL RESULT | PASS | FAIL | COMMENTS | QA PERSON
QA: |  | Start Date: | End Date: | Time:
HM1 | MY BOOKING | On my booking page display | Should have below options
|  |  | Option to login with user name and password |  | Pass
Option to enter Reference number and E mail ID or Phone number
HM1.1 | Login |  |  |  | Pass
HM1.1.1 | Correct Data | Enter correct user name and password | Successful login with welcome message |  | Pass |  | welcome message not found
HM1.1.2 | Wrong Data | Enter wrong user name and password | Login failure with message "Invalid user name or password" |  | Pass
HM1.2 | Successful Login | My booking page display | My booking page will have the below details
|  |  | Upcoming hotel bookings |  | Pass
|  |  | Completed hotel bookings |  | Pass
|  |  | My Profile |  | Pass
HM1.2.1 | Upcoming Hotel Bookings | If no booking available | Show 'No upcoming hotel bookings' message on the page |  | Pass
|  | If any bookings available | It should show the nearest upcoming hotel booking in detail |  | Pass
HM1.2.1.1 | Hotel details | On display of One room hotel | Hotel Image |  | Pass
|  |  | Hotel name and address |  | Pass
|  |  | Check in date |  | Pass
|  |  | Check out date |  | Pass
|  |  | No. of rooms (should be displayed as one ) and no. of nights |  | Pass
|  |  | No. of persons |  | Pass
|  |  | Total price |  | Pass
|  |  | Status |  | Pass
|  | On display of two room hotel | Hotel image |  | Pass
|  |  | Hotel name and address |  | Pass
|  |  | Check in date |  | Pass
|  |  | Check out date |  | Pass
|  |  | No. of rooms (should be displayed as two ) and no. of nights |  | Pass
|  |  | No. of persons |  | Pass
|  |  | Total price |  | Pass
|  |  | Status |  | Pass
HM1.2.1.2 | View voucher | Click on View voucher menu | It should display the voucher in a new tab |  | Pass
HM1.2.1.3 | Cancel voucher (if applicable) | Click on the menu 'Cancel voucher' | A pop should be displayed which should read "Are you sure you want to cancel this voucher?". And user should select 'Cancel' or 'Confirm' |  | Fail |  | when we click cancel e mail was send to cancel
|  | On 'Cancel' option from pop up | No change in the status |  | Pass
|  | On 'Confirm' option from pop up and on successful cancellation | Status should be changed to 'Waiting for Refund' |  | Pass
|  |  | An e mail notification should be send to admin on hotel cancellation |  | Pass |  | e mail was delayed
In the admin 'Hotel online booking' section, the status of the particular booking should be changed to 'Waiting for Refund'
|  | On 'Confirm' option from pop up and cancellation failed | A pop response should be displayed as 'Cancellation Failed, please contact our customer care executive for immediate assistance'
An e mail notification should be send to admin on hotel cancellation failure with hotel details, booking ID and customer details
|  | On changing the status from Admin to Refunded | The status should be changed to 'Refunded' on My Booking
HM1.2.1.4 | The Grid View | On display of One room hotel | The grid view of upcoming hotels should show below fields: Reference ID, check in, check out, Booking Date, Status and View option |  | Pass
HM1.2.1.5 | View Option | On selection of view button from the grid | Selected booking should be expanded to show the details and to View voucher and Cancel voucher |  | Pass
HM1.2.1.6 | Status in details section and on grid | If the voucher is successful | 'Booked' status will be displayed |  | Pass |  | status is vouchered
|  | If the voucher is failed after payment | 'Waiting for refund' status should be displayed |  | Pass
|  | If cancelled | 'Waiting for refund' status should be displayed |  | Pass
|  | If the voucher is canceled and refunded | 'Refunded' status should be displayed |  | Pass
HM1.2.2 | Completed Hotel Bookings | If no booking available | Show 'No completed hotel bookings' message on the page |  | Pass
|  | If any bookings available | It should show the latest completed hotel booking in detail |  | Pass
|  |  | other completed hotel bookings in a grid with a view option |  | Pass
HM1.2.2.1 | Hotel details | On display of one room hotel | Hotel Image |  | Pass
|  |  | Hotel name and address |  | Pass
|  |  | Check in date and Check out date |  | Pass
|  |  | No. of rooms (should be displayed as one ) and no. of nights |  | Pass
|  |  | No. of persons |  | Pass
|  |  | Total price |  | Pass
|  |  | Status of the booking |  | Pass
|  | On display of two room hotel | Hotel image |  | Pass
|  |  | Hotel name and address |  | Pass
|  |  | Check in date and Check out date |  | Pass
|  |  | No. of rooms (should be displayed as two ) and no. of nights |  | Pass
|  |  | No. of persons |  | Pass
|  |  | Total price |  | Pass
|  |  | Status of the booking |  | Pass
HM1.2.2.2 | View voucher | Click on View voucher menu | It should display the voucher in a new tab |  | Pass
HM1.2.2.3 | The Grid View | On display | The grid view of completed hotels should show below fields: Reference ID, check in, check out, Booking Date, Status and View option |  | Pass |  | also destination
HM1.2.2.4 | View Option | On selection of view button from the grid | The selected booking should be expanded to show the details and to View voucher and Cancel voucher |  | Pass
Pass
HM1.2.2.5 | Grid Status | If the voucher is successful | 'Booked' status will be displayed |  | Pass
|  | If the voucher is failed | 'Waiting for refund' status should be displayed |  | Pass
|  | If cancelled | 'Waiting for refund' status should be displayed |  | Pass
|  | If the voucher is canceled and refunded | 'Refunded' status should be displayed |  | Pass
HM 1.3 | My Booking | Enter correct Reference ID and E mail ID | Show the respective booking details |  | Pass
|  | Enter correct Reference ID and Phone number | Show the respective booking details |  | Pass
|  | Enter wrong Reference ID and /or E mail ID | Show the message 'No bookings available for the given details. Please check the data are correct'. |  | Pass
|  | Enter wrong Reference ID and /or Phone Number | Show the message 'No bookings available for the given details. Please check the data are correct'. |  | Pass
HM 1.3.1 | On entry of corrct details |  |  |  | Pass
HM1.3.1.1 | Hotel details | On display of One room hotel | Hotel Image |  | Pass
|  |  | Hotel name and address |  | Pass
|  |  | Check in date |  | Pass
|  |  | Check out date |  | Pass
|  |  | No. of rooms (should be displayed as one ) and no. of nights |  | Pass
|  |  | No. of persons |  | Pass
|  |  | Total price |  | Pass
|  |  | Status |  | Pass
|  | On display of two room hotel | Hotel image |  | Pass
|  |  | Hotel name and address |  | Pass
|  |  | Check in date |  | Pass
|  |  | Check out date |  | Pass
|  |  | No. of rooms (should be displayed as two ) and no. of nights |  | Pass
|  |  | No. of persons |  | Pass
|  |  | Total price |  | Pass
|  |  | Status |  | Pass
HM1.3.1.2 | View voucher | Click on View voucher menu | It should display the voucher in a new tab |  | Pass
HM1.3.1.3 | Cancel voucher (if applicable) | Click on the menu 'Cancel voucher' | A pop should be displayed which should read "Are you sure you want to cancel this voucher?". And user should select 'Cancel' or 'Confirm' |  | fail
|  | On 'Cancel' option from pop up | No change in the status
|  | On 'Confirm' option from pop up and on successful cancellation | Status should be changed to 'Waiting for Refund'
An e mail notification should be send to admin on hotel cancellation
In the admin 'Hotel online booking' section, the status of the particular booking should be changed to 'Waiting for Refund'
|  | On 'Confirm' option from pop up and cancellation failed | A pop response should be displayed as 'Cancellation Failed, please contact our customer care executive for immediate assistance'
An e mail notification should be send to admin on hotel cancellation failure with hotel details, booking ID and customer details
|  | On changing the status from Admin to Refunded | The status should be changed to 'Refunded' on My Booking