## Sheet1
CASE ID | MODULE | DESCRIPTION | Result | Commets | Bug posted
| Hotel | Verifying Hotel voucher with all providers.
|  | Checked 'Hotel' proceed with multiple room. | Fail | Cant proceed from room details page. | Issue already posted.
|  | Checked hotel voucher with 'Hotelbeds_' provider. | Fail | On the provider response have no results it says. 'Quota exceeded'
|  | Checked hotel voucher with 'Dotw_' provider. | Fail | Ticket Not occure in frontent , on froend end showing 'Booking Failed' and the transaction was vouchered in backend. | #32983
|  | Checked hotel voucher with 'TBO_1' provider. | Fail | Ticket Not occure in frontent , on froend end showing 'Booking Failed' and the transaction was vouchered in backend. | #32983
|  | Checked hotel voucher with 'Expedia_Test' provider. | Fail | Ticket Not occure in frontent , on froend end showing 'Booking Failed' and the transaction was vouchered in backend. | #32983
|  | Checked hotel voucher with 'Rida_test' provider. |  | No Result Found , No log Generating
|  | Checked hotel voucher with 'Vervotech_' provider. |  | No Result Found , No log Generating
|  | Checked hotel voucher with 'InventoryHotelProvider' provider. | Fail | Ticket Not occure in frontent , on froend end showing 'Booking Failed' and the transaction was vouchered in backend. | #32983
|  | Checked hotel voucher with 'RezliveOtram_' provider. |  | No result Occuring, Checked rezlive provider in 'Attar travel, Booksultan' result not getting.
|  | Checked the 'My Booking' for the Hotel with the 'Ref ID & Email'. | Pass | Got the hotel transaction with the refference.
|  | Checked the View ticket option available in the My booking | Pass | Redirected to voucher page.
|  | Checked the Cancel Ticket option available in the My booking | Pass | Cancellation mail send success.
|  | Checked the send mail, print ticket, save ticket option available in the 'view ticket' through opened voucher. | Pass
| Hotel TQR / Booking Actions | Checked the each tabs for the hotel transaction in TQR | Fail | Payment Details & GST Details Tab have Issue. | #33006
|  | Checked the Print ticket option in the HOTEL TQR. | Fail | Redirected to voucher page. also some times shows 401 page, 500 error page. | Issue already posted.
| Transfer | Checked Transfer Ticket with 'TransferzProvider_' provider. | Pass | Got transfer ticket [In round trip single pax/multi pax].
|  | Checked proceed to ticket with 'One way'. | Fail | Not getting Ticket 'Booking Failed' Occuring. | Issue already posted.
|  | Checked the Transfer result after proceed from result page. | Fail | Result change while proceed to passenger details page. | #32985
|  | Checked Transfer Ticket with 'HB_Transfer' provider. with Round Trip. | Pass | [Got Ticket]
|  | Checked proceed to ticket with 'One way'. | Pass | [Got Ticket]
Pending
Hotel, Transfer, Activity Booking Action
Rezlive Hotel provide currently not get result
Need to check 'InventoryTransferProvider_' for ticketing
My booking for Transfer, Activity.
My booking cancelation working for hotel.
Verify multi-language.
TQR edit